## Slide 1: PAM NORTHERN CHAPTER Seminar on Practical Construction Law TIME IN CONSTRUCTION CONTRACT Penang, 21st December 2019
LIM HOCK SIANG
Presgrave & Matthews

## Slide 2
The Question of TIME in Construction Contract:-
  Date of Commencement or Date of Possession of Site?
  Date of Completion of the whole Works or sections of the Works?
  Damages for Non-Completion
  Extension of Time (EOT)
  Loss & Expense Claims

## Slide 3: What is the meaning of “Time is of the Essence”?
  S. 56(1) of the Contracts Act 1950 provides:-
  “When a party to a Contract promises to do a certain thing on or before a specified time, … and fails to do any such thing at or before the specified time, the Contract, or so much of it as has not been performed, becomes voidable at the option of the promisee, if the intention of the parties was that time should be of the essence of the contract.”

## Slide 4: Is Time of the Essence in PAM 2018 (without Quantities) ?
Clause 21.1:-
“On the Date of Commencement, possession of the Site shall be given to the Contractor who shall commence the execution of the Works and regularly and diligently proceed with and complete the same on or before the Completion Date.”

## Slide 5: What is the consequence if time for completion of the Works is of the essence and the Contractor fails to complete the Works by the stipulated time?
Section 56(1):-
“… becomes voidable at the option of the promisee …”

## Slide 6: Does PAM 2018 gives the Employer a right to terminate the Contract if the Contractor fails to carry out the Works timely?
Clause 25.1:-
“ The Employer may determine the employment of the Contractor if:-
(a) without reasonable cause, wholly or substantially suspends the carrying out of the Works before completion;
(b) fails to proceed regularly and diligently with the Works.”

## Slide 7: What if the Contract does not state the time for completion of the Works?
Time at LARGE
Completion within reasonable time under section 47 of the Contracts Act 1950

## Slide 8: In a Contract where time is not of the essence, what are the Employer’s entitlement in the event that the Contractor fails to complete the Works by the completion date?
General Damages
S56(2):- if it was not the intention of the parties that time should be of the essence of the contract, the contract does not become voidable by the failure to do the thing at or before the specified time; but the promisee is entitled to compensation from the promisor for any loss occasioned to him by the failure.
Burden of Proof is on the Employer to prove actual damage.

## Slide 9: What does PAM 2018 provides?
Clause 22.0:- “Liquidated Damages calculated at the rate stated in the Appendix”
What is the pre-condition?
Certificate of Non-Completion (CNC)
Lion Engineering Sdn Bhd v Pauchuan Development Sdn Bhd [1997] 4 AMR 3315; Kerajaan Malaysia v KCSB Konsortium Sdn Bhd [2019] 10 MLJ 429
    The purpose of CNC is “to prevent time from being at large after the completion date has set in and to justify a claim for LAD”

## Slide 10: What if the Appendix omits to state the rate of liquidated damages?
    Not enforceable
    Contra proferentem
    General Damages

## Slide 11: When should CNC be issued?
Clause 22.1
The Architect shall issue a CNC:-
(a) upon the failure of the contractor to complete within the Completion Date or extended completion date; and
(b) “the Architect is of the opinion that the same ought reasonably to have been completed.”

## Slide 12: What are the Employer’s remedies after issuance of CNC under PAM 2018?
Clause 22.1 – the Employer may:-
(a) recover such sum as a debt, or
(b) deduct such sum from any monies due, or
(c) recover such sum from Performance Bond.

## Slide 13: What are the procedure requirements to deduct liquidated damages under PAM 2018?
Clause 22.1 – “the Employer shall inform the Contractor in writing of such deduction …”
Set-Off procedures under Clause 30.4 and Adjudication are not applicable.

## Slide 14: Is the Employer required to prove actual loss when recovering liquidated damages?
s 75 of the Contracts Act 1950 provides:-
  “When a contract has been broken, if a sum is named in the contract as the amount to be paid in case of such breach, or if the contract contains any other stipulation by way of penalty, the party complaining of the breach is entitled, whether or not actual damage or loss is proved to have been caused thereby, to receive from the party who has broken the contract reasonable compensation not exceeding the amount so named or, as the case may be, the penalty stipulated for.”

## Slide 15: The previous position before 2019
Innocent party must prove the actual loss and damage suffered unless the case falls under the situation where it is difficult to assess actual damage or loss.
    Selva Kumar a/l Murugiah v Thiagarajah a/l Retnasamy [1995] 1 MLJ 817
    Johor Coastal Development Sdn Bhd v Constrajaya Sdn Bhd [2009] 4 MLJ 445

## Slide 16: Would it be difficult to assess the loss arising from delayed completion in building Contract?
YES
Keen Builders Sdn Bhd v Utara Dua (Malaysia) Sdn Bhd [1998] 2 CLJ Supp 256
No
Clarity Heights Sdn Bhd v Syarikat Samland Sdn Bhd [1999] 4 MLJ 485
UF Engineers Sdn Bhd v Sribonus Sdn Bhd
Kejuruteraan Bintai Kindenko Sdn Bhd v Serdang Baru Properties Sdn Bhd

## Slide 17: Position after 2019
Cubic Electronics Sdn Bhd v MARS Telecommunications Sdn Bhd [2019] 6 MLJ 15
  Federal Court adopts the English Law approach in Cavendish Square Holding BV v Talal El Makdessi [2015] UKSC 67, SC.
  Principle of law on damages clause are equally applicable to forfeiture of deposit.

## Slide 18: The present legal position on whether proof of actual loss is required?
“No necessity for proof of actual loss or damage in every case where the innocent party seeks to enforce damages clause.”
“Reasonable compensation is not confined to actual loss, although evidence of that may be a useful starting point.”

## Slide 19: The legal burden …
“Initial onus” lies on:-
(i) a Claimant of Liquidated Damages that there was a breach of contract, and
(ii) the Contract contains a clause specifying a sum to be paid upon breach.
“Once the above is established, the innocent party is entitled to receive a sum not exceeding the amount stated … subject to the defaulting party proving the unreasonableness of the damages clause including the sum stated therein.”

## Slide 20: How do you determine whether the sum payable as LD is unreasonable?
In determining what is reasonable compensation, the concepts of “legitimate interest” and “proportionality” as enunciated in Cavendish are relevant.
“A sum payable on breach of contract will be held to be unreasonable compensation if it is extravagant and unconscionable in amount in comparison with the highest conceivable loss which could possibly flow from the breach”

## Slide 21
“… The Court to adopt a common sense approach …”
“… to derive reasonable compensation there must not be a significant difference between the level of damages spelt out in the Contract and the level of loss or damage which is likely to be suffered by the innocent party.”

## Slide 22: Are the relative bargaining position of parties relevant in the determination of the reasonableness of LD clause?
  “… Courts are reluctant to interfere with parties’ freedom of contract, especially if the contracting parties have comparable bargaining power and are properly advised …”
  “… the Courts should be slow to refuse to give effect to a damages clause for contracts which are the result of thorough negotiations made at arm’s length between parties who have been properly advised …”

## Slide 23: The question of legitimate interest, proportionality and reasonableness is to be adjudged from what point in time?
  “ … reasonable compensation can be deduced by comparing the amount that would be payable on breach with the loss that might be sustained if indeed the breach occurred …”
  Suggest that the question is to be adjudged at the time of making of contract.

## Slide 24: Is the Contractor precluded by Clause 22.2 from challenging the reasonableness of LD clause?
  “… a court of law has always maintained a supervisory jurisdiction to relieve against a damage clause which is so unconscionable or oppressive …”
  “…the legislative mechanism introduced by s75 of the Act must be considered as a necessary curtailment of absolute freedom of contract, designed to check against potential abuse by a party at another’s expense.”

## Slide 25: Is actual loss still relevant?
  Evidence of actual loss “a useful starting point” to show reasonable compensation.
  “ … except possibly in the case of situations where one of the parties to the contract is able to dominate the other as to the choice of the terms of a contract, it will normally be insufficient to establish that a provision is objectionably penal … where the application of the provision could result in a larger sum being recovered by the injured party than his actual loss. Even in such situations, so long as the sum payable … is not extravagant, having regard to the range of losses that it could reasonably be anticipated … at the time the contract was made, can still be a genuine pre-estimate of the loss …”

## Slide 26: What happens if the sum provided is found to be unreasonable or disproportionate?
General Damages
Court determine reasonable compensation

## Slide 27
EXTENSION OF TIME CLAUSES
Time for completion becomes at large if there is no contractual provision which confer power on the S.O/Architect to extend the date of completion on the occurrence of delay events within the obligation of the Employer.
    Thamesa Designs Sdn Bhd & Ors v Kuching Hotels Sdn Bhd [1993] 3 MLJ 25

## Slide 28: Procedure for EOT Application
Clause 23.1(a):-
Submit Notice of Intention to claim extension of time within 28 days from the date of the relevant event.
Initial estimate of EOT required
Particulars of the cause of delay

## Slide 29
Clause 23.1(b):-
Submit final claim for extension of time within 28 days of the end of the cause of delay.
Particulars of delay to enable the Architect to assess EOT.

## Slide 30
Clause 23.3
Within 28 days of receipt of final claim for EOT under Clause 23.1(b), the Architect must notify the Contractor if particulars submitted are insufficient to assess EOT.
Clause 23.4
Within 6 weeks from the receipt of final EOT claim with sufficient particulars, Architect issue Certificate of EOT with details.

## Slide 31
Failure to comply is fatal unless it is waived.
  - City Inn Ltd v Shepherd Construction [2003] ScotCS 146
  - NH International (Caribbean) Ltd v National Insurance Property Development Co Ltd [2015]
  - PKNS Engineering Construction Bhd v Global Inter-Dream (M) Sdn Bhd [2014] 5 MLJ 206
Does the Contractor losses right of claim if Clause 23.1(a) and (b) are not complied?

## Slide 32: Is the Contractor precluded from claiming EOT for failing to give timely notification if delay was caused by the Employer?
“… but such work was ordered by the Architect … and was for the benefit of the developer and in pursuance of the contract … The Architect, therefore, must have had knowledge of the apparentness of such delay, and the Architect therefore require no notice or early notice of such delay brought by himself.”
    Syarikat Tan Kim Beng & Rakan-Rakan v Pulai Jaya Sdn Bhd [1992] 1 MLJ 42

## Slide 33
In Gaymark Investments Pty Ltd v Walter Construction Group Ltd (1999) NTSC 143, the Australia Court held that it would result in an “entirely unmeritorious award of liquidated damages” to the Employer just because of the failure to comply with the notice provision since the Employer had caused the delay in the first instance.

## Slide 34
Clause 23.10 confers a discretionary power to grant EOT 12 weeks after CPC, whether or not Clause 23.1 has been complied with by the Contractor.
  “The Architect may within twelve (12) weeks after the date of CPC review and fix a Completion Date later than that previously fixed, if in his opinion the fixing of such later Completion Date is fair and reasonable … and whether or not a Relevant Event has been specifically notified by the Contractor under Clause 23.1 …”

## Slide 35: Quantum of Extension of Time
  The principle of assessing EOT is that the period of EOT reflects the effect of Delay Events on the completion date.
  - Gasing Heights v Pilecon (2000) 1 MLJ 621
  The Contractor must establish causal link for each and every delay event.
  Delayed progress per se is not sufficient.
  Delay must be of an activity which is on the critical path to completion.
  -Lim Chin San Contractors Pte Ltd v LW Infrastructure Pte Ltd (2011)

## Slide 36: Whether the Contractor must establish delay through Critical Path analysis?
“The absence of a critical path analysis does not mean there was no evidence before the Arbitrator to assess EOT …”
    Top Speed Holding Sdn Bhd v Conlay Construction Sdn Bhd [2011] MLJU 121

## Slide 37: Works Programme
  Clause 3.5 requires the Contractor to submit Works Programme “showing the order in which he proposes to carry out the Works”.
  Clause 3.7 says that the Works Programme may be relied by the Architect as a basis for the assessment of extension of time and the effect of the delay and/or disturbances to the progress of the Works.
  Clause 3.6 :- Works Programme shall not constitute part of the Contract

## Slide 38: Why Works Programme is stipulated as not part of the Contract?
  If a programme were to be made a Contract Document, it has the effect of making the commencement and completion time of each and every activity shown therein of the essence.
  Any departure will constitute a breach of contract.
  Impractical

## Slide 39: What is the meaning of FLOAT in Works Program?
  Float is basically the time available for an activity in addition to its actual duration required to perform that activity.
  Allocation of buffer time for a particular work activity in the preparation of a programme to cater for uncertainties or risks.

## Slide 40
The Society of Construction Law (“SCL”) Delay and Disruption Protocol (2002) defines:-
“Float” – Time available for an activity in addition to its planned duration.
“Free Float” – The amount of time that an activity can be delayed beyond its early start/ early finish dates without delaying the early start or early finish of any immediate following activity.
“Total Float” – The amount of time that an activity may be delayed beyond its early start/early finish without delaying the contract completion date.

## Slide 42
Who owns the Float in a Programme?
  Contract is King.
  PAM 2018 does not deal expressly with ownership of Float.
  Putrajaya Conditions of Main Contract (Clause 43.07) provides that Float time within work schedule belongs to the Employer.

## Slide 43
3 possible scenarios :-
(1) Contractor owns the Float – Contractor may use it to absorb delays occasion by events which he may not be entitled to EOT.
(2) Employer owns the Float – S.O. may use it to reduce EOT that the contractor would otherwise be entitled to.

## Slide 44
(3) The Project owns the Float – “First Come First Served” rule.
- If there are 2 event of delays, one is an event of delay by Employer and the other is an event of delay by the Contractor, the entitlement to the Float depends on which of the 2 events of delay occurs first.

## Slide 45
Cont.
- If the event of delay by the Employer occurs first in time thereby using up the Float and there is not enough Float to cater for Contractor’s subsequent event of delay, Contractor will be liable for LAD.
- Conversely, in the event of delay by the Contractor occurs first in time, the Contractor would then be entitled to EOT.

## Slide 46
The school of thought that Float belongs to Project
SCL Protocol
Ascon Contracting v Alfred McAlpine (UK) [1999] ALL ER (D) 1147
Weaver-Bailey Constractors v United States 19 Cl. Ct. 474 (1990)

## Slide 47
Variation to the rule on Float belongs to Project?
The Royal Brompton Alexander Hospital v Frederick Alexander Hammonl and others [2000]:-
Employers get the benefit of Float if Contractors does not need it. But if Contractor incurs any other later delaying events and he is liable to LAD, the ownership of float goes back to the Contractor.

## Slide 48
Is the Contractor entitled to EOT arising from an Employer’s delay event if the Contractor is also responsible for delay?
If a relevant event involves overlapping Works which can be carried out simultaneously or concurrently with other Works and has no delay effect on the date of completion, the Contractor is NOT entitled to EOT.

## Slide 49
In Gasing Heights Sdn Bhd v Pilecon (2000) 1 MLJ 621, the High Court held that in assessing EOT, concurrent delay must be taken into consideration.
The issue of concurrent delay was held to have arisen because although the Architect issued an instruction to change the location of the TNB sub-station which is a relevant event, the Contractor delayed in complying with the instruction.

## Slide 50
Society of Construction Law Protocol states that “true concurrent delay is the occurrence of two or more delay events at the same time, one as an Employer Risk Event and the effect of which are felt at the same time.”
The delaying events must be critical.

## Slide 51
Example:-
No work is possible on Site for 1 week, delaying the completion of the Work by 1 week due to 2 causative events which happened at the same time.
    (i) One is a Relevant Event, i.e. inclement weather which renders no work on site possible.
    (ii) Non-Relevant Event, i.e. the Contractor did not have any workers and work could not proceed at all during that week.

## Slide 52
Henry Boot Construction v Malmaison Hotel (1999) 70 Con LR 32
Parties agreed that if there are two concurrent causes of delay, one of which is a relevant event, and the other is not, then the Contractor is entitled to an extension of time for the period of delay caused by the relevant event notwithstanding the concurrent effect of the other event.

## Slide 53
Royal Brompton Hospital v Hammond
Contractor is not entitled to EOT in situation where Work was already delayed by a Contractor’s default, and a relevant event then occurs which, had the Contractor not been delayed, would have caused them delay but which, because of the existing delay, it made no difference.

## Slide 54
Jerram Falkus Construction Ltd v Fenice Investments [2011]:-
“If there are two concurrent causes of delay, one which was the Contractor’s responsibility, and one which was said to trigger the prevention principle, the principle would not in fact be triggered because the Contractor could not show that the Employer’s conduct made it impossible for him to complete within the stipulated time. The existence of a delay for which the Contractor is responsible, covering the same period of delay which was caused by an act of prevention, would mean the Employer had not prevented actual completion.”

## Slide 55
Example:-
(a) The Contractor is many months in delay due to own default.
(b) The Employer then issue V.O instruction to change colour of wall from red to blue.
(c) The paint which took 5 weeks to be procured, was delivered before the completion of the wall.
Is the Contractor entitled to EOT?

## Slide 56
Adyard Abu Dhabi v SD Marine Services:-
“Common sense tells the observer that such an extension of time was neither fair nor reasonable, where the Employer’s actions have not actually delayed the progress of the Contractor by a single day.”

## Slide 57
Is the Contractor entitled to EOT based on:-
(1) The Contractor did not complete the Work by 12/09/1989 due to its own default.
(2) Between February – July 1990, while the Contractor was in culpable delay, the Employer instructed variations.
Balfour Beatty v Chestermount Properties:-
    EOT based on “net basis” which is calculated based on period required to carry out VOs added on to the Completion date. “Dotting on approach”.
    Not “gross basis”, wherein EOT period will run from original completion date to the date at which the effect of the delaying event ends.

## Slide 58
City Inn v Shepherd Construction (2012):-
“If a dominant cause can be identified as the cause of some particular delay in the completion of the Works, effect will be given to that … depending on whether or not the dominant cause is a relevant event, the claim for EOT will or will not succeed.”
“When a situation exists in which two causes are operative, it may be operative to apportion.”

## Slide 59
Can the Architect grant an extension of time after the issuance of CNC?
- Clause 23.9 – “Net basis”

## Slide 60
“Consequences of Improper Administration or Misapplication of EOT provision in Contract, time for completion set at large.”
- Kerajaan Malaysia v Ven-Coal Resources Sdn Bhd [2014] 5 CLJ 186

## Slide 61
Thank You For Your Time
Presented by Lim Hock Siang
Partner of Messrs. Presgrave & Matthews